## Sheet1
|  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  | Week 9 | [5 empty] | Week 10
|  | MA | DI | WO | DO | VR | MA | DI | WO | DO | VR | MA | DI | WO | DO | VR | MA | DI | WO | DO | VR | MA | DI | WO | DO | VR | MA | DI | WO | DO | VR | MA | DI | WO | DO | VR | MA | DI | WO | DO | VR | MA | DI | WO | DO | VR | MA | DI | WO | DO | VR
Documentation | 2 weeks | bar: MA to Week 2 VR
Research | 2 weeks | bar: Week 2 MA to Week 3 VR; Week 4 DI to Week 4 VR
program the machine | 2 weeks | bar: Week 4 MA to Week 6 VR
Test the machine | 1 week | bar: Week 6 MA to Week 7 VR
Shoulds and coulds(if possible due to time) | 1 week | bar: Week 7 MA to Week 8 VR
Preparing Presentation | 1 day | bar: Week 9 MA
eventually fix some last minute problems | 4 days | bar: Week 9 DI to Week 9 VR